|  |  |  |  |
| --- | --- | --- | --- |
| № | Activity | Rel. | Estimate |
| 1 | Client Meeting |  | 1 day |
| 2 | Case and Client Research |  | 1 day |
| 3 | Problem Formulation and Description | 2,1 | 1 day |
| 4 | Research Method |  | 1 day |
| 5 | Applied Theory |  | 1 day |
| 5.1 | Research for applied theory. |  | 0.5 day |
| 5.2 | Writing the applied theory. |  | 0.5 day |
| 6 | User Research. |  | 7 days |
| 6.1 | Quantitative research |  | 1 day |
| 6.2 | Qualitative research |  | 3 days |
| 6.2.1 | Making an Interview Guide/Categorising users. |  | 0.5 day |
| 6.2.2 | Conducting Interviews. | 6.2.1 | 1 day |
| 6.2.3 | Internet Research for qualitative information |  | 0.5 day |
| 6.2.4 | Analysing interviews. | 6.2.2 | 0.5 day |
| 6.2.5 | Analysing the information gathered from the internet.( Quantitative and Qualitative) | 6.2.3 | 0.5 day |
| 7 | Writing the conclusions, we made for the website in Problem Solution | 6 | 0.5 day |
| 8 | Creating first prototype.(Sketch) | 7.1 | 0.5 day |
| 8.1 | Reviewing the protype. | 7.2 | 0.5 day |
| 8.2 | Refining the prototype. | 7.2.1 | 0.5 day |
| 9 | Creating the second prototype.(Wireframe) | 7.2.2 | 0.5 day |
| 9.1 | Reviewing the protype. | 7.3 | 0.5 day |
| 9.2 | Refining the prototype. | 7.3.1 | 0.5 day |
| 10 | Creating the third prototype.(Mock-up) | 7.3.2 | 0.5 day |
| 10.1 | Reviewing the protype. | 7.4 | 0.5 day |
| 10.2 | Refining the prototype. | 7.4.1 | 0.5 day |
| 11 | Coding the website. | 7.4.2 | 3 days |
| 12 | Think out-loud test | 7.5 | 1 day |
| 12.1 | Analysing the test | 7.6 |  |
| 12.2 | Making changes if needed | 7.6.1 |  |
| 13 | Completing the problem solution. | 7.6.2 | 0.5 day |
| 14 | Finishing the report | 7.7 | 0.5 day |
| 14.1 | Writing Conclusion |  |  |
| 14.2 | Writing Perspectivation |  |  |
| 14.3 | Writing Process Reflection |  |  |
| 14.4 | Adding the references used and all the relevant information in Appendices. |  |  |
| 15 | Preparation for the exam |  | 1 day |
| 15.1 | Creating a presentation |  | s |